## Slide 1
YEARS 11–12 WORK STUDIES · YEAR 11 · M09
Team Enterprise Project
Plan, deliver and evaluate a purposeful team enterprise.
BEFORE WE BEGIN
Where might these ideas affect a real workplace, pathway or life decision?
M09 · Team Enterprise Project
01
Notes: Teaching focus: Establish the purpose of Team Enterprise Project.
Talking points
- Plan, deliver and evaluate a purposeful team enterprise.
- Name the three learning areas without teaching them yet: Defining the problem and project purpose; Planning roles, resources, risks and communication; Delivering, evaluating and presenting enterprise evidence.
- This deck supports learning and formative evidence. It does not replace current teacher directions or assessment notices.
- Visual notice: Notice how each path leads to a different work context. What would you need to learn about yourself and the setting before choosing?
Prompt: Ask students where the module could affect a real decision, then collect two or three examples.
Transition: Move from the purpose to the three-part learning map.
[Sources]
- NSW Work Studies Stage 6 Content Endorsed Course syllabus: https://library.curriculum.nsw.edu.au/341419dc-8ec2-0289-7225-6db7f2d751ef/8fda1536-85d8-4b5e-83cd-387160b95ca1/work-studies-stage-6-cec-2012.pdf
- Teacher-posted source: stage-01/sources/Module 9 - course support PDF
- Approved learning package: specialists/learning/course-content.js (SHA-256 1562e52eb7e549764869cf2bd90394e38177901e146f17e8b74e035bca13bf9e)
- Visual: specialists/visuals/web-ready/course-orientation.webp | original AI-generated raster | SHA-256 60539a909cbb5bb58ab0a9b03d8b22631666fa97c9f417ed06dcdd419d8c5605
[/Sources]

## Slide 2
YEARS 11–12 WORK STUDIES · YEAR 11 · M09
Three ideas build one practical understanding
01
Defining the problem and project purpose
Define a manageable team enterprise project from a verified need, stakeholder evidence and clear success indicators.
02
Planning roles, resources, risks and communication
Coordinate a team enterprise project through accountable roles, sequenced work, resource control, risk management and communication.
03
Delivering, evaluating and presenting enterprise evidence
Evaluate an enterprise project through outcome evidence, teamwork learning and an honest account of decisions and limitations.
Retrieval lens · After each idea, explain what decision it improves and what evidence makes the explanation credible.
M09 · Team Enterprise Project
02
Notes: Teaching focus: Preview the three named sections as a connected learning sequence.
Talking points
- 1. Defining the problem and project purpose: Define a manageable team enterprise project from a verified need, stakeholder evidence and clear success indicators.
- 2. Planning roles, resources, risks and communication: Coordinate a team enterprise project through accountable roles, sequenced work, resource control, risk management and communication.
- 3. Delivering, evaluating and presenting enterprise evidence: Evaluate an enterprise project through outcome evidence, teamwork learning and an honest account of decisions and limitations.
Prompt: Ask students to predict which section will be most useful in the next year and explain why.
Transition: Begin with Defining the problem and project purpose.
[Sources]
- NSW Work Studies Stage 6 Content Endorsed Course syllabus: https://library.curriculum.nsw.edu.au/341419dc-8ec2-0289-7225-6db7f2d751ef/8fda1536-85d8-4b5e-83cd-387160b95ca1/work-studies-stage-6-cec-2012.pdf
- Teacher-posted source: stage-01/sources/Module 9 - course support PDF
- Approved learning package: specialists/learning/course-content.js (SHA-256 1562e52eb7e549764869cf2bd90394e38177901e146f17e8b74e035bca13bf9e)
[/Sources]

## Slide 3
YEARS 11–12 WORK STUDIES · YEAR 11 · M09
Defining the problem and project purpose
The official module asks students to apply teamwork and enterprise skills through a project that resembles workplace situations. A strong project begins with a problem statement: who experiences what need, in which context, and what evidence shows it matters? Scope makes the project manageable.
APPLY AND SHOW
Problem-to-proposal sprint. Use a fictional or teacher-approved need to create a problem statement, stakeholder map, three alternative responses, scope boundary, deliverable and five indicators. Evidence: A one-page proposal canvas and 90-second team pitch.
Notice: Notice what the team is photographing, sorting and tracing. What evidence would help define the problem more precisely?
You can show this when: I can write a problem statement that separates need from a preferred solution.
M09 · Team Enterprise Project
03
Notes: Teaching focus: Define a manageable team enterprise project from a verified need, stakeholder evidence and clear success indicators.
Talking points
- The official module asks students to apply teamwork and enterprise skills through a project that resembles workplace situations. A project might explore a good, service, event, simulated business, community initiative or school support, but a possibility is not approval. The project, external contact, identity use, money, facilities, data and safety arrangements are Teacher to confirm. Until approval is explicit, students can complete a planning-only simulation using fictional stakeholders and costs.
- A strong project begins with a problem statement: who experiences what need, in which context, and what evidence shows it matters? Beginning with a favourite solution can cause solution fixation, where the team defends an idea before understanding the need. Stakeholder interviews, observations, existing records and small tests can clarify the problem, provided privacy and approval boundaries are followed. A purpose statement then describes the useful change the project intends to create without claiming an outcome that has not occurred.
- Scope makes the project manageable. It identifies inclusions, exclusions, time, resources, decision authority and constraints. Goals translate purpose into intended results; indicators describe evidence that would show progress or achievement. Both product or service outcomes and learning outcomes matter. A proposal should therefore connect problem, purpose, deliverable, stakeholders, scope, resources, risks, indicators and approval gates before implementation begins.
- Worked example — Scoping a reusable-resource initiative: A team wants to 'fix waste at school' by selling reusable kits. The claim is broad, no waste evidence has been collected and sales are not approved. The team narrows the problem to a hypothetical pattern of disposable items at one event, identifies users and organisers, and proposes an approved audit or simulated dataset. It compares kit, communication and process-change options rather than locking into sales. The proposal defines a small deliverable, exclusions, indicators and approval gates. The project remains planning-only unless the teacher confirms implementation.
- Visual caption: A project purpose should answer an observed need, not merely justify a solution the team already prefers.
- Visual notice: Notice what the team is photographing, sorting and tracing. What evidence would help define the problem more precisely?
- Applied evidence: Use a fictional or teacher-approved need to create a problem statement, stakeholder map, three alternative responses, scope boundary, deliverable and five indicators. Mark every approval dependency Teacher to confirm. A one-page proposal canvas and 90-second team pitch.
Prompt: Test whether each indicator could provide usable evidence.
Likely misconception or nuance
- A project proposal is strongest when it promises to solve the biggest possible problem. Correction: A credible proposal defines a bounded need, achievable deliverable, evidence and authority; exaggerated scope weakens feasibility and accountability.
Transition: Move to Planning roles, resources, risks and communication.
[Sources]
- NSW Work Studies Stage 6 Content Endorsed Course syllabus: https://library.curriculum.nsw.edu.au/341419dc-8ec2-0289-7225-6db7f2d751ef/8fda1536-85d8-4b5e-83cd-387160b95ca1/work-studies-stage-6-cec-2012.pdf
- Teacher-posted source: stage-01/sources/Module 9 - course support PDF
- Approved learning package: specialists/learning/course-content.js (SHA-256 1562e52eb7e549764869cf2bd90394e38177901e146f17e8b74e035bca13bf9e)
- Visual: specialists/visuals/web-ready/m09-s01.webp | original AI-generated raster | SHA-256 1621a23a0e3659a665dbb8f6192e6980babfddc1036ef4f6d4bb74cdcda972a3
[/Sources]

## Slide 4
YEARS 11–12 WORK STUDIES · YEAR 11 · M09
Planning roles, resources, risks and communication
Team planning converts a proposal into coordinated action. An action plan sequences tasks and shows dependencies—work that cannot begin until another task or approval is complete. Risk and communication are continuous, not one-off forms.
APPLY AND SHOW
Enterprise control-room simulation. Turn the approved or hypothetical proposal into a role matrix, dependency plan, milestone timeline, resource register, risk log and meeting record. Evidence: A coordinated project-control pack and individual accountability note.
Notice: Notice the role, timeline, resource, risk and device cues. Which dependency could delay the rest of the plan?
You can show this when: I can allocate roles by task needs, capability and workload rather than status.
M09 · Team Enterprise Project
04
Notes: Teaching focus: Coordinate a team enterprise project through accountable roles, sequenced work, resource control, risk management and communication.
Talking points
- Team planning converts a proposal into coordinated action. Roles should make responsibility visible without isolating information or allowing one person to dominate. A role allocation can consider capability, learning goals, availability and workload, with backup arrangements for critical tasks. Responsibility means owning the next action and reporting evidence; accountability remains shared where team decisions affect the whole project. Meeting records capture decisions, actions, owners and due dates rather than reproducing every spoken word.
- An action plan sequences tasks and shows dependencies—work that cannot begin until another task or approval is complete. Milestones mark meaningful progress, while a resource register tracks people, time, materials, equipment, information and any approved funds. Estimates should include contingencies and actual use should be recorded. A project can fail even when each individual is busy if critical dependencies, approvals or shared resources are not managed.
- Risk and communication are continuous, not one-off forms. The team reviews safety, financial, operational, privacy, reputational and participation risks as conditions change. A change request states what is proposed, why, impact on scope, time, resources and risk, and who can approve it. Communication is matched to audience and purpose, and disagreement is resolved through evidence, shared goals and agreed decision rules. Local tools, contacts and authorisation levels are Teacher to confirm.
- Worked example — Recovering a slipping event simulation: A team planning a simulated careers event has attractive promotion drafts but no confirmed session plan. The venue task depends on teacher approval and one member holds all stakeholder notes. The team maps dependencies, pauses promotion claims that rely on unconfirmed details and redistributes the notes to an approved shared location. Roles are reallocated by workload and capability, with one owner and backup for each critical task. A change request reduces the simulated event scope and updates milestones, risks and messages. The response targets the bottleneck rather than blaming the busiest-looking member.
- Visual caption: A deliverable plan connects who will act, what they need, when it happens, what may go wrong and how the team will stay informed.
- Visual notice: Notice the role, timeline, resource, risk and device cues. Which dependency could delay the rest of the plan?
- Applied evidence: Turn the approved or hypothetical proposal into a role matrix, dependency plan, milestone timeline, resource register, risk log and meeting record. Respond to a supplied disruption through a documented change request. A coordinated project-control pack and individual accountability note.
Prompt: Approve or reject a change and update all affected records.
Likely misconception or nuance
- Good teamwork means everyone completes exactly the same amount of every task. Correction: Fair teamwork allocates clear, meaningful contributions according to task need, capability, learning and workload, then makes accountability and support visible.
Transition: Move to Delivering, evaluating and presenting enterprise evidence.
[Sources]
- NSW Work Studies Stage 6 Content Endorsed Course syllabus: https://library.curriculum.nsw.edu.au/341419dc-8ec2-0289-7225-6db7f2d751ef/8fda1536-85d8-4b5e-83cd-387160b95ca1/work-studies-stage-6-cec-2012.pdf
- Teacher-posted source: stage-01/sources/Module 9 - course support PDF
- Approved learning package: specialists/learning/course-content.js (SHA-256 1562e52eb7e549764869cf2bd90394e38177901e146f17e8b74e035bca13bf9e)
- Visual: specialists/visuals/web-ready/m09-s02.webp | original AI-generated raster | SHA-256 c58e773a0f5683013c36ab20b52e04ecb61c371d43477017dd172dc8639a993d
[/Sources]

## Slide 5
YEARS 11–12 WORK STUDIES · YEAR 11 · M09
Delivering, evaluating and presenting enterprise evidence
Delivery is controlled implementation, not simply finishing a product. Evaluation compares what was intended with what occurred and explains why. A project presentation should make reasoning visible.
APPLY AND SHOW
Evidence-to-story showcase. Use an approved or fictional project evidence pack to build a five-part presentation: need, action, adaptation, result and next step. Evidence: A public-safe presentation storyboard, indicator table and individual reflection.
Notice: Notice the before-and-after photographs, checklist and stakeholder discussion. What evidence supports a claim that the project helped?
You can show this when: I can compare results with baseline, goals and indicators.
M09 · Team Enterprise Project
05
Notes: Teaching focus: Evaluate an enterprise project through outcome evidence, teamwork learning and an honest account of decisions and limitations.
Talking points
- Delivery is controlled implementation, not simply finishing a product. Teams monitor quality, schedule, resources, participation and risk while recording decisions and changes. Evidence may include approved observations, counts, feedback, version history, meeting actions and product checks. The collection method should be proportional, privacy-safe and aligned with the indicator. More evidence is not automatically better if it is irrelevant, inconsistent or collected without authority.
- Evaluation compares what was intended with what occurred and explains why. Outcome evidence assesses the effect of the deliverable; process evidence assesses planning, communication and problem-solving; learning evidence shows growth in teamwork and enterprise skills. Attribution should be cautious: a positive change after a project does not prove the project caused all of it. Limitations, unexpected effects and stakeholder differences belong in a credible evaluation.
- A project presentation should make reasoning visible. It can move from need and purpose to proposal, implementation, adaptations, evidence, evaluation and next steps. Claims should match the strength of evidence, and setbacks should be analysed rather than hidden. Individual reflection identifies a specific contribution, feedback, learning and transfer to future work. Approved public-safe artefacts can illustrate the story; personal data, unapproved images, private messages and fabricated testimonials must be excluded.
- Worked example — Evaluating a simulated orientation resource: A team creates a prototype orientation guide. Five test users find information faster, but two pages remain confusing and only one test group was involved. The team compares completion time and feedback with its baseline and reports the small sample as a limitation. It explains the page redesign and shows version evidence. It does not claim the guide will work for every user or that the project is authorised for public release. Each member links an individual contribution and feedback to a transferable work skill.
- Visual caption: Evaluation is persuasive when the delivered outcome, evidence of change and feedback can be examined together.
- Visual notice: Notice the before-and-after photographs, checklist and stakeholder discussion. What evidence supports a claim that the project helped?
- Applied evidence: Use an approved or fictional project evidence pack to build a five-part presentation: need, action, adaptation, result and next step. Include one limitation and an individual transfer statement. A public-safe presentation storyboard, indicator table and individual reflection.
Prompt: Add one limitation, adaptation and transferable learning statement.
Likely misconception or nuance
- A successful presentation should hide every setback. Correction: Credible enterprise evidence explains setbacks, responses and limitations because adaptation and honest evaluation demonstrate workplace learning.
Transition: Move from the three teaching sections into retrieval.
[Sources]
- NSW Work Studies Stage 6 Content Endorsed Course syllabus: https://library.curriculum.nsw.edu.au/341419dc-8ec2-0289-7225-6db7f2d751ef/8fda1536-85d8-4b5e-83cd-387160b95ca1/work-studies-stage-6-cec-2012.pdf
- Teacher-posted source: stage-01/sources/Module 9 - course support PDF
- Approved learning package: specialists/learning/course-content.js (SHA-256 1562e52eb7e549764869cf2bd90394e38177901e146f17e8b74e035bca13bf9e)
- Visual: specialists/visuals/web-ready/m09-s03.webp | original AI-generated raster | SHA-256 0fe0fafa3e8898077ed9a4163a18fd784cc40852dd8c0c1a266d7c482b2666d8
[/Sources]

## Slide 6
YEARS 11–12 WORK STUDIES · YEAR 11 · M09
Retrieve the idea, then explain the reason
Answer without notes first. Use one precise evidence-based sentence for each check.
01
Why should a problem statement avoid naming the preferred solution?
02
What is the best basis for allocating team roles?
03
Why is a baseline needed for evaluation?
A calm checking cycle
1 Recall from memory
2 Check the matching section
3 Correct the reason
4 Try the question again
M09 · Team Enterprise Project
06
Notes: Teaching focus: Retrieve and repair reasoning across all three sections.
Talking points
- Give quiet recall time before opening the discussion.
- Check 1: It keeps the need open to investigation and comparison of alternatives. Rationale: Separating problem and solution reduces fixation.
- Check 2: Task requirements considered with capability, learning goals, availability and balanced workload. Rationale: Role allocation should support both delivery and fair participation.
- Check 3: It provides a starting point against which later results can be compared. Rationale: Without a baseline, the scale and direction of change are harder to judge.
Prompt: Ask students to justify an answer before checking the matching theory section.
Transition: Use the retrieved ideas to construct one sustained evidence response.
[Sources]
- NSW Work Studies Stage 6 Content Endorsed Course syllabus: https://library.curriculum.nsw.edu.au/341419dc-8ec2-0289-7225-6db7f2d751ef/8fda1536-85d8-4b5e-83cd-387160b95ca1/work-studies-stage-6-cec-2012.pdf
- Teacher-posted source: stage-01/sources/Module 9 - course support PDF
- Approved learning package: specialists/learning/course-content.js (SHA-256 1562e52eb7e549764869cf2bd90394e38177901e146f17e8b74e035bca13bf9e)
[/Sources]

## Slide 7
YEARS 11–12 WORK STUDIES · YEAR 11 · M09
Build evidence that makes your reasoning visible
Evaluate a team enterprise project using outcome, process and learning evidence, then propose a justified next step.
01
READ
Identify the command verb and the relationship.
02
SELECT
Choose relevant course evidence.
03
EXPLAIN
Connect evidence to a supported judgement.
04
CHECK
Answer every part and test the criteria.
CHECK YOUR RESPONSE
• Integrates product, process and learning evidence.
• Keeps claims within the evidence and acknowledges limitations.
Notice the different evidence types and how they are organised. Which item shows the work, and which item helps explain the learning?
M09 · Team Enterprise Project
07
Notes: Teaching focus: Guide one higher-order response anchored in Delivering, evaluating and presenting enterprise evidence.
Talking points
- Prompt: Evaluate a team enterprise project using outcome, process and learning evidence, then propose a justified next step.
- Compare baseline, goals, indicators and actual results.
- Explain important decisions, adaptations and team processes using evidence.
- Assess attribution, stakeholder differences, limitations and unintended effects.
- Recommend the next step and identify your transferable individual learning.
- Success criteria: Integrates product, process and learning evidence.; Keeps claims within the evidence and acknowledges limitations.; Uses only approved, privacy-safe material in the proposed presentation.
- Folio visual: A useful folio brings work samples, observations, records and reflection together so progress can be explained.
Prompt: Ask students to state their judgement before selecting evidence, then test whether every claim is supported.
Transition: Close with a three-part exit record and a clear evidence boundary.
[Sources]
- NSW Work Studies Stage 6 Content Endorsed Course syllabus: https://library.curriculum.nsw.edu.au/341419dc-8ec2-0289-7225-6db7f2d751ef/8fda1536-85d8-4b5e-83cd-387160b95ca1/work-studies-stage-6-cec-2012.pdf
- Teacher-posted source: stage-01/sources/Module 9 - course support PDF
- Approved learning package: specialists/learning/course-content.js (SHA-256 1562e52eb7e549764869cf2bd90394e38177901e146f17e8b74e035bca13bf9e)
- Visual: specialists/visuals/web-ready/folio-evidence.webp | original AI-generated raster | SHA-256 0d3e88f590077ba563b8f3dd06a0c2c9a2975bdd4b4a3b8294cdc877d6dd366d
[/Sources]

## Slide 8
YEARS 11–12 WORK STUDIES · YEAR 11 · M09
Leave with evidence and one useful next step
01
RECALL
Name one idea you can now explain accurately.
02
EVIDENCE
Record the detail that makes your explanation convincing.
03
NEXT
Save the slide 7 response, then note one question about delivering, evaluating and presenting enterprise evidence.
Save this as formative learning evidence. It is not an assessment submission. Follow the current teacher notice for any formal task.
M09 · Team Enterprise Project
08
Notes: Teaching focus: Create a concrete learning record while keeping the assessment boundary explicit.
Talking points
- Students complete all three exit prompts before discussion.
- The saved response is formative learning evidence, not a formal submission.
- Assessment-orientation visual: The task brief sets the requirements; work evidence and reflection show how those requirements were addressed.
Prompt: Notice the three sources being compared. What could each contribute to a fair explanation of achievement?
Likely misconception or nuance
- Saving learning evidence does not automatically submit it for assessment or prove achievement.
Transition: End with each student's stated next question or action.
[Sources]
- NSW Work Studies Stage 6 Content Endorsed Course syllabus: https://library.curriculum.nsw.edu.au/341419dc-8ec2-0289-7225-6db7f2d751ef/8fda1536-85d8-4b5e-83cd-387160b95ca1/work-studies-stage-6-cec-2012.pdf
- Teacher-posted source: stage-01/sources/Module 9 - course support PDF
- Approved learning package: specialists/learning/course-content.js (SHA-256 1562e52eb7e549764869cf2bd90394e38177901e146f17e8b74e035bca13bf9e)
- Visual: specialists/visuals/web-ready/assessment-orientation.webp | original AI-generated raster | SHA-256 78b88ec22b90ac0135ac756df19012e62644e6174e0988f1df2848e74d2b2ce1
[/Sources]